## Task List
Date | Resource | Planned task | Planned completion date | Status | Issue | Actions taken to resolve issue
2018-02-12 | Alma | Format Work Ethic Reports | 2020-02-14 | Done
2018-02-12 | Alma | Create Vacancy Report |  | Busy | Lots of formulas
2018-02-14 | Alma | Format Work Ethic Reports |  | Busy
2018-02-15 | Alma | Format Work Ethic Reports |  | Busy
2018-02-16 | Alma | Upload W/E Reports to UAT |  | Busy
2018-02-17 | Alma
2018-02-18 | Alma
2018-02-19 | Alma | Leave Reports, Vacancy Age analysis |  | Busy
2018-02-20 | Alma | Leave Reports, Vacancy Age analysis |  | Busy
2018-02-21 | Alma | Work Ethics Reports |  | Done
2018-02-22 | Alma | Leave View UBA, Create Leave Planning View |  | Done
2018-02-23 | Alma | Load Query Tool Leave Reports |  | Done
2018-02-24 | Alma
2018-02-25 | Alma
2018-02-26 | Alma | Load Leave reports on UBA |  | Done
2018-02-27 | Alma
2018-02-28 | Alma | Internal Couple, Vacancy Age Load 10.16 |  | Done
2018-03-01 | Alma | Relief & Redeploy Reports |  | Done
2018-03-02 | Alma
2018-03-03 | Alma
2018-03-04 | Alma
2018-03-05 | Alma
2018-03-06 | Alma
2018-03-07 | Alma

## Reports to complete
Report No | Reporting Area | Phase | Report Name | RPT File Name | Environment Loaded On (UAT/PreProd/Prod) | Reason Not Completed
1 | Work Ethics | Phase 1 | Disciplinary Hearing Notice
2 | Work Ethics | Phase 1 | Written Warning | YSANC006
3 | Work Ethics | Phase 1 | Letter Template or Disciplinary/Sanctions
4 | Work Ethics | Phase 1 | Sanction report
5 | Work Ethics | Phase 1 | Credit Recovery Suspension | YSANC009
6 | Work Ethics | Phase 1 | Minutes of Disciplinary Committee | YMINDISCOM
7 | Work Ethics | Phase 1 | Exoneration Letter | YSANC020
8 | Work Ethics | Phase 1 | Final Warning Letter | YSANC005
9 | Work Ethics | Phase 1 | Letter of Caution | YSANC002
10 | Work Ethics | Phase 1 | Letter of Displeasure | YSANC008
11 | Work Ethics | Phase 1 | Recall from Suspension Letter | YRECSUSPEN
12 | Work Ethics | Phase 1 | Suspension Letter | YSANC011
13 | Work Ethics | Phase 1 | Suspension Pending Investigation
14 | Work Ethics | Phase 1 | Warning Letter | YSANC006
15 | Work Ethics | Phase 1 | Disciplinary Report | YDISREP
16 | Work Ethics | Phase 1 | Withdrawal of Sanction Letter | YWDRAWSANC
17 | Work Ethics | Phase 1 | Declaration of Secrecy | YDECSEC
18 | Work Ethics | Phase 1 | Password Security Undertaking | YPASSEC
19 | Work Ethics | Phase 1 | Asset Declaration Form | YASSDEC
20 | Work Ethics | Phase 1 | Grievance Closure Letter | YGRIEVCLOLET
21 | Work Ethics | Phase 1 | Grievance Final Correspondence | YGRIVEFINCOR
22 | Work Ethics | Phase 1 | Grievance Holding Letters | YGRIEVLET
23 | Work Ethics | Phase 1 | Grievance Report
24 | Work Ethics | Phase 2 | Approval for CBN Return Cover Letter
25 | Work Ethics | Phase 2 | CBN-Return Cover Letter
26 | Work Ethics | Phase 2 | CBN Layout/template
27 | Work Ethics | Phase 2 | Fraud Reporting - CBN
28 | Work Ethics | Phase 1 | Letter template for commendation
29 | Work Ethics | Phase 1 | Commendation report