## Task List
Date | Resource | Planned task | Planned completion date | Status | Issue | Actions taken to resolve issue
2018-02-02 | Work ethics: sanc001 - sanc020 | Testing on 10,16 and uba | 2018-02-02 | Loaded on uba | not printing
2018-02-05 | HR Onboarding | Testing on 10,16 , making changes to margins TOTAL OF 21 REPORTS | 2018-02-06 | Loaded on uba | non
2018-02-06 | AS ABOVE | AS ABOVE | 2018-02-07 | Loaded on uba | non
2018-02-07 | HR GEOGRAPHICS | SQL, CRYSTAL DESIGN, TOTAL OF 5 REPORTS | 2018-02-10
2018-02-08 | HR GEOGRAPHICS | SQL, CRYSTAL DESIGN, TOTAL OF 5 REPORTS | 2018-02-11
2018-02-09 | HR GEOGRAPHICS | SQL, CRYSTAL DESIGN, TOTAL OF 5 REPORTS | 2018-02-12 | DONE | NON
2018-02-12 | HR GEOGRAPHICS | TESTING 10,15 | 2018-02-13
2018-02-13 | HR GEOGRAPHICS | TESTING 10,16 | 2018-02-14 | DONE | NON
2018-02-14 | HR GEOGRAPHICS | UPLOADED TO UBA AND TESTING | 2018-02-15 | UBA

## Reports to complete
Report No | Reporting Area | Phase | Report Name | Environment Loaded On (UAT/PreProd/Prod) | Reason Not Completed
1 | HR Onboarding | Phase 1 | Arrival Documents | UAT
2 | HR Onboarding | Phase 1 | Offer Letter | UAT
3 | HR Onboarding | Phase 1 | Onboarding Form | UAT
4 | HR Onboarding | Phase 2 | Recruitment & Confirmation Checklist | UAT
5 | HR Onboarding | Phase 1 | Interview Rating Forms | UAT
6 | HR Onboarding | Phase 1 | New Employee Profile Form | UAT (Tested)
7 | HR Onboarding | Phase 1 | Offer Letter Template | UAT
8 | HR Onboarding | Phase 1 | Declaration of Secrecy | UAT (Tested)
9 | HR Onboarding | Phase 1 | Letter if Authority to Pay Employee Net Indebtedness to Bank | UAT
10 | HR Onboarding | Phase 1 | Password Secrecy Undertaking | UAT (Tested)
11 | HR Onboarding | Phase 1 | Guarantor Form | UAT (Tested)
12 | HR Onboarding | Phase 1 | Related Party Form | UAT
13 | HR Onboarding | Phase 1 | Account Opening Form | UAT (Tested)
14 | HR Onboarding | Phase 1 | National Housing Form | UAT (Tested)
15 | HR Onboarding | Phase 1 | Asset Declaration Form | UAT (Tested)
16 | HR Onboarding | Phase 1 | Recruitment/Confirmation Checklist | UAT (Tested)
17 | HR Onboarding | Phase 2 | CBN Form for AGMs & Above
1 | HR Demographics | Phase 1 | Group Staff Distribution by nationality & Location during YYYY FY | UAT
2 | HR Demographics | Phase 1 | Staff Distribution by Location | UAT
3 | HR Demographics | Phase 1 | Staff Distribution by Gender | UAT
4 | HR Demographics | Phase 1 | Staff Distribution by Nationality | UAT
5 | HR Demographics | Phase 1 | Gender Analysis per Grade & Designation | UAT
1 | HR Medical | Phase 1 | Avon Medical Template | Prod (busy Testing)
2 | HR Medical | Phase 1 | Avon Medical Template Changes | Prod (busy Testing)
3 | HR Medical | Phase 1 | Avon Medical Staff Dependants Exit Template for Above 18 | Prod (busy Testing)
4 | HR Medical | Phase 1 | Avon Medical Staff Hospital Exits Template | Prod (busy Testing)
5 | HR Medical | Phase 1 | Avon Medical Report - Deleted Dependants | Prod (busy Testing)
1 | Payroll | Phase 1 | Department Wise NHF Details | Busy (Received info)
2 | Payroll | Phase 1 | Pensions Report | Busy (Received info)
3 | Payroll | Phase 1 | Monthly Cost Analysis Report | Busy (Received info)
4 | Payroll | Phase 1 | Updates Report | Requested example
5 | Payroll | Phase 1 | Payment Details Report
6 | Payroll | Phase 1 | Pay register Details Report
7 | Payroll | Phase 1 | Employees Compensation Act (ECA) Report Schedule
8 | Payroll | Phase 1 | Nigeria Branch Operations Staff Cost Report
9 | Payroll | Phase 1 | Head Office Operations Staff Cost
10 | Payroll | Phase 1 | Nigeria Branch IT Staff Cost No
11 | Payroll | Phase 1 | Nigeria HQ IT Staff Cost No
12 | Payroll | Phase 1 | Salaries & Wage per Grade & Designation
13 | Payroll | Phase 1 | Defined Contribution per Grade & Designation
14 | Payroll | Phase 1 | Salaries/Wages Band Stratification
15 | Payroll | Phase 1 | Remuneration to the Group's Directors
16 | Payroll | Phase 1 | Directors' Benefits Band Stratification
NOTE: | All work ethics done and was taken over by Alma and some was redone by her from the end of December 2017 and Hershlin added some information