## Revised List
Leave Report List 2017 | [14 empty] | Priority List | Complete
[15 empty] | None | Yes
[15 empty] | Low | No
[15 empty] | Medium | Descope/Moved Out
Number | Section | Report ID | Reports Name | Comments/Notes | Specification | Suggested Resource | Effort Required (in Days) | Resources Effort Used | Priority | Due Date | Date Tested/UAT/PATCH | Date Delivered/Complete | Overdue by (Days) Formula - DO NOT CHANGE | Complete? | High
1 | Leave | 032 | Currently on leave report showing all categories of leave |  | On Sample | Tsego | 3 |  |  | 2017-11-15 |  |  | 0 | Yes
2 | Leave | 033 | Due to resume |  | On Sample | Tsego | 1 |  |  | 2017-11-15 |  |  | 0 | Yes
3 | Leave | 034 | Commenced leave within the period |  | On Sample | Tsego | 1 |  |  | 2017-11-15 |  |  | 0 | Yes
4 | Leave | 035 | Leave pending approval report |  | On Sample | Tsego | 1 |  |  | 2017-11-15 |  |  | 0 | Yes
5 | Leave | 036 | Leave allowance report |  | On Sample | Tsego | 1 |  |  | 2017-11-15 |  |  | 0 | Yes
6 | Leave | 037 | Leave plan report |  | On Sample | BP | 2 |  |  | 2017-11-15 |  |  | 0 | No
7 | Leave | 038 | Utilized plan leave report |  | On Sample | BP | 1 |  |  | 2017-11-15 |  |  | 0 | No
8 | Leave | 039 | Leave plan outstanding report |  | On Sample | BP | 1 |  |  | 2017-11-15 |  |  | 0 | No
9 | Leave | 040 | Recalled leave report | Duplicate Report No Days | On Sample | BP | 0 |  |  | 2017-11-15 |  |  | 0 | No
10 | Leave | 041 | Leave balance report by date |  | On Sample | BP | 2 |  |  | 2017-11-15 |  |  | 0 | No
11 | Leave | 042 | Approved outstanding leave days report |  | On Sample | BP | 1 |  |  | 2017-11-15 |  |  | 0 | No
12 | Leave | 043 | Maternity leave exception report by date for unconfirmed staff |  | On Sample | BP | 1 |  |  | 2017-11-15 |  |  | 0 | No
13 | Leave | 044 | Staff relief report |  | On Sample | BP | 2 |  |  | 2017-11-15 |  |  | 0 | No
14 | Leave | 045 | Leave exception report for confirmed and unconfirmed staff |  | On Sample | BP | 3 |  |  | 2017-11-15 |  |  | 0 | No
15 | Leave | 046 | Unutilised leave report |  | On Sample | BP | 1 |  |  | 2017-11-15 |  |  | 0 | No
16 | Leave | 047 | Resumption log | Duplicate of Due to Resume? | On Sample | BP | 0 |  |  | 2017-11-15 |  |  | 0 | No
17 | Leave | 048 | Leave Recall |  | On Sample | BP | 1 |  |  | 2017-11-15 |  |  | 0 | No
18 | Leave | 049 | Absence Tracker |  | On Sample | BP | 3 |  |  | 2017-11-15 |  |  | 0 | No
19 | Leave | 050 | Annual Leave Utilisation Tracker |  | On Sample | BP | 2 |  |  | 2017-11-15 |  |  | 0 | No
20 | Leave | 051 | Maternity leave tracker - summary |  | On Sample | BP | 3 |  |  | 2017-11-15 |  |  | 0 | No
21 | Leave | 052 | Maternity leave tracker – Staff profile |  | On Sample | BP | 3 |  |  | 2017-11-15 |  |  | 0 | No
22 | Leave | 053 | Leave Compliance |  | On Sample | BP | 3 |  |  | 2017-11-15 |  |  | 0 | No
23 | Leave | 054 | All Leave Uptake |  | On Sample | BP | 3 |  |  | 2017-11-15 |  |  | 0 | No
24 | Leave | 055 | Number of leave taken, leaves per quarter |  | Outstanding | BP | 3 |  |  | 2017-11-15 |  |  | 0 | No
25 | Leave | 056 | Exception reports to line managers and HR |  | Outstanding | BP | 3 |  |  | 2017-11-15 |  |  | 0 | No
26 | Leave | 057 | Study leave | Can be Combined with Master Leave Report | On Sample | BP | 0 |  |  | 2017-11-15 |  |  | 0 | No
27 | Leave | 058 | Staff due for resumption |  | On Sample | BP | 3 |  |  | 2017-11-15 |  |  | 0 | No
28 | Leave | 059 | Sick leave report | Can be Combined with Master Leave Report | On Sample | BP | 0 |  |  | 2017-11-15 |  |  | 0 | No
29 | Leave | 060 | Leave of absence | Can be Combined with Master Leave Report | On Sample | BP | 0 |  |  | 2017-11-15 |  |  | 0 | No
30 | Leave | 061 | Annual Leave | Master Leave Report With Filters | On Sample | BP | 3 |  |  | 2017-11-15 |  |  | 0 | No
31 | Leave | 062 | Casual Leave | Can be Combined with Master Leave Report | On Sample | BP | 0 |  |  | 2017-11-15 |  |  | 0 | No
32 | Leave | 063 | Compassionate leave | Can be Combined with Master Leave Report | On Sample | BP | 0 |  |  | 2017-11-15 |  |  | 0 | No
33 | Leave | 064 | Examination leave | Can be Combined with Master Leave Report | On Sample | BP | 0 |  |  | 2017-11-15 |  |  | 0 | No
34 | Leave | 065 | Paternity Leave | Can be Combined with Master Leave Report | On Sample | BP | 0 |  |  | 2017-11-15 |  |  | 0 | No
35 | Leave | 066 | Medical leave report | Can be Combined with Master Leave Report | On Sample | BP | 0 |  |  | 2017-11-15 |  |  | 0 | No
36 | Leave | 067 | Extended Sick Leave | Can be Combined with Master Leave Report | On Sample | BP | 0 |  |  | 2017-11-15 |  |  | 0 | No
37 | Leave | 068 | Leave provision per employee |  | On Sample | BP | 2 |  |  | 2017-11-15 |  |  | 0 | No
38 | Leave | 069 | Managers to see balance of outstanding leave days of employees |  | On Sample | BP | 3 |  |  | 2017-11-15 |  |  | 0 | No
39 | Leave | 070 | Excessive leave balances |  | On Sample | BP | 1 |  |  | 2017-11-15 |  |  | 0 | No
40 | Leave | 071 | Negative leave |  | On Sample | BP | 1 |  |  | 2017-11-15 |  |  | 0 | No
41 | Leave | 072 | Notification for sick leave in observation period |  | On Sample | BP | 2 |  |  | 2017-11-15 |  |  | 0 | No
42 | Leave | 073 | Maternity Leave exception for confirmed staff |  | On Sample | BP | 1 |  |  | 2017-11-15 |  |  | 0 | No
Maternity Leave