## Task List
Date | Resource | Planned task | Planned completion date | Status | Issue | Actions taken to resolve issue
02-02-2018 | Recall From Suspension - YRECSUSPEN | Getting work ethics up to date | 09-02-2018 | updated and checked, ready for testing | missing fields | changed view, added nickname and sequence number
| Grievance Holding Letters - YGRIEVLET | Getting work ethics up to date | 09-02-2018 | updated and checked, ready for testing | missing fields | changed view, added nickname and sequence number
| Grievance Final Correspondence - YGRIVEFINCOR | Getting work ethics up to date | 09-02-2018 | updated and checked, ready for testing | missing fields | changed view, added nickname and sequence number
| Grievance Closure Letter - YGRIEVCLOLET | Getting work ethics up to date | 09-02-2018 | updated and checked, ready for testing | missing fields | changed view, added nickname and sequence number
05-02-2018 | Recall From Suspension - YRECSUSPEN | Getting work up to date to Almas specifications | 09-02-2018 | checked | different connection, did not look like Almas reports | changed report setup, updated connection
| Grievance Holding Letters - YGRIEVLET | Getting work up to date to Almas specifications | 09-02-2018 | checked | different connection, did not look like Almas reports | changed report setup, updated connection
| Grievance Final Correspondence - YGRIVEFINCOR | Getting work up to date to Almas specifications | 09-02-2018 | checked | different connection, did not look like Almas reports | changed report setup, updated connection
| Grievance Closure Letter - YGRIEVCLOLET | Getting work up to date to Almas specifications | 09-02-2018 | checked | different connection, did not look like Almas reports | changed report setup, updated connection
| Minutes Of Disiplinary - YMINDISCOM | Getting work up to date to Almas specifications | 09-02-2018 | checked | different connection, did not look like Almas reports | changed report setup, updated connection
| Federal Mortgage - YFEDMOR | Edit and update | 09-02-2018 | checked | data was moving around when printed from system | changed margins and size of text inputs
06-02-2018 | Minutes Of Disiplinary - YMINDISCOM | Edit, update, check and test | 09-02-2018 | completed and checked, ready for testing | no links to subreports | created links to subreports
| Declaration Of Secrecy - YDECSEC | Edit, update, check and test | 09-02-2018 | updated and checked, ready for testing | lines jumping out of margins | changed lines by using underscores instead of fullstops
| Related Parties Declaration - YRELPARDEC | Edit, update, check and test | 09-02-2018 | updated and checked, ready for testing | margins are too big, lines jumping out of margins | adjusted margins to the correct size, changed lines by using underscores instead of fullstops
| Letter Of Authority - YLETAUT | Edit, update, check and test | 09-02-2018 | updated and checked, ready for testing | margins are too big, lines jumping out of margins | adjusted margins to the correct size, changed lines by using underscores instead of fullstops
| Related Parties Tracker - YRELPARTRAC | Edit, update, check and test | 09-02-2018 | updated and checked, ready for testing | had to make columns smaller | adjusted colunm sizes
| Withdrawal Of Sanction - YWDRAWSAN | Edit, update, check and test | 09-02-2018 | edited and checked, ready for testing | had to be created as report could not be found | created the report acording to Almas specifications
| Credit Recovery Suspension - YCREDRECSUS | Edit, update, check and test | 09-02-2018 | edited and checked, ready for testing | has to be redone to Almas specifications | created the report acording to Almas specifications
07-02-2018 | Credit Recovery Suspension - YCREDRECSUS | Edit,update | 09-02-2018 | edited and checked, ready for testing | report was found to be a duplicate to a sanction report | report was scraped
| Grievance Letter - GRIEVLET | Test | 09-02-2018 | tested X3 printing | Was not printing | Had to update links and add SeqNum parameter
| Grievance Final Corresspondance - GRIEVFINCOR | Test | 09-02-2018 | tested X3 printing | Was not printing | Had to update links and add SeqNum parameter
| Grivance Closure Letter - GRIEVCLOLET | Test | 09-02-2018 | tested X3 printing | Was not printing | Had to update links and add SeqNum parameter
| Minutes Of Disiplinary Committee - YMINDISCOM | Edit,update,check and test | 09-02-2018 | edited and checked, ready for testing | Was not printing | Had to create groups withi subreports
08-02-2018+F31A24:F32A24:F27A24:G27A24A24:G27 | Letter Of Commendation | Test | 09-02-2018 | tested X3 printing | editing according to Almas specification | edited according to almas specification
| Minutes Of Disiplinary Committee - YMINDISCOM | Test | 09-02-2019 | tested X3 printing | Was not printing | updated links to datatbase
| Recall From Suspension - YRECSUSPEN | Test | 09-02-2020 | tested X3 printing | Was not printing | had to update empty date fields
| Withdrawal Of Sanction - YWDRAWSANC | Test | 09-02-2021 | tested X3 printing | Was not printing | had to update date and comment fields
09-02-2018 | Query Letter - YQUERY | Test | 09-02-2018 | tested X3 printing | Was not printing | updated links to datatbase
| Termination Notice Of Disengagement - YTERMNOTOFDISEN | Test | 09-02-2018 | tested X3 printing | needed to edit format | changed to almas specifications
| Mapping of payroll reports as well as gathering examples to work from | Gathering as much information as possible to start with payroll next week | 09-02-2018 | mapped out more or less the information we may need | very few report examples | requested for more examples
12-02-2018 | Planning out payroll reports, finding required data to create views etc | Planning how to tackle payroll reports | 16-02-2018 | gathered some reports, delegated workload between Riaan and myself | not all report examples are obtained | requested for more examples and financial information
| Validation Exception Report | write query for this payroll report | 16-02-2018 | query has been written | missing validation information as I don’t know what validation is to be used | requested for information about this issue, waiting for information and examples
13-02-2018 | Medical Consent - YMEDCONSNT | TEST | 09-02-2018 | tested X3 | waiting to be uploaded to UBA for testing | sent through to be uploaded to UBA
| PREEMPLOYMENT MEDICAL LETTER - YPREEMPMEDLET | TEST | 09-02-2018 | tested X3 | waiting to be uploaded to UBA for testing | sent through to be uploaded to UBA
| ECA Form 1 - YECA1 | TEST | 09-02-2018 | tested X3 | waiting to be uploaded to UBA for testing | sent through to be uploaded to UBA
| ECA Form 1 - YECA2 | TEST | 09-02-2018 | tested X3 | waiting to be uploaded to UBA for testing | sent through to be uploaded to UBA
| ECA Form 1 - YECA3 | TEST | 09-02-2018 | tested X3 | waiting to be uploaded to UBA for testing | sent through to be uploaded to UBA
| ECA Form 1 - YECA4 | TEST | 09-02-2018 | tested X3 | waiting to be uploaded to UBA for testing | sent through to be uploaded to UBA
| Summary Dismissal Nil Balance - YSUMDISNILBAL | TEST | 09-02-2018 | tested X3 | waiting to be uploaded to UBA for testing | sent through to be uploaded to UBA

## Reports to complete
Report No | Reporting Area | Phase | Report Name | Environment Loaded On (UAT/PreProd/Prod) | Reason Not Completed
1 | HR Confirm | UBA Team Only | Confirmation Database report
2 | HR Confirm | UBA Team Only | Deferment report
3 | HR Confirm | UBA Team Only | Former employment reference report
4 | HR Confirm | UBA Team Only | Guarantor report
5 | HR Confirm | UBA Team Only | Result verification report |  | NEED TO UPDATE REPORT
6 | HR Confirm | UBA Team Only | Periodic Confirmation report
7 | HR Confirm | UBA Team Only | Existing staff background check report
8 | HR Confirm | UBA Team Only | CBN new hires clearance report
9 | HR Confirm | UBA Team Only | Confirmation Appraisal Report
1 | HR Exit | UBA Team Only | Exit Checklist Template
2 | HR Exit | UBA Team Only | Staff Exit Template
3 | HR Exit | UBA Team Only | History of Exit Requests
4 | HR Exit | UBA Team Only | Letter of Resignation (indebtedness & benefit)
5 | HR Exit | UBA Team Only | Terminal Account - Benefit
6 | HR Exit | UBA Team Only | Terminal Account - Indebtedness
7 | HR Exit | UBA Team Only | Terminal Account -Retirement
8 | HR Exit | UBA Team Only | Exit Interview Form
9 | HR Exit | UBA Team Only | Exit Clearance Checklist & List of Clearance Stakeholders
10 | HR Exit | UBA Team Only | Letter of Termination – Credit Balance
11 | HR Exit | UBA Team Only | Letter of Termination – Debit Balance
12 | HR Exit | UBA Team Only | Letter of Dismissal - No Benefit
13 | HR Exit | UBA Team Only | Letter of Dismissal – No Benefit
14 | HR Exit | UBA Team Only | Letter of Dismissal – Debit Balance
1 | HR Redeploy | UBA Team Only | Redeployment Letter
1 | HR Relief | UBA Team Only | Relief Assignment Letter
7 | HR Medical | UBA Team Only | Dependant Details
8 | HR Medical | UBA Team Only | Staff Official Details
9 | HR Medical | UBA Team Only | Medical Consent
10 | HR Medical | UBA Team Only | Pre-employment Medical letter
11 | HR Medical | UBA Team Only | ECA forms
12 | HR Medical | UBA Team Only | Staff Personal Details
Note on D2: hershlin naidoo: WAS NOT ON LIST FROM UBA TEAM
Note on D3: hershlin naidoo: CHECK WITH ALMA
Note on D4: hershlin naidoo: CHECK WITH ALMA
Note on D5: hershlin naidoo: CHECK WITH ALMA
Note on D6: hershlin naidoo: NEED TO UPDATE INFORMATION
Note on D7: hershlin naidoo: CHECK WITH ALMA
Note on D8: hershlin naidoo: WAS NOT ON LIST FROM UBA TEAM
Note on D9: hershlin naidoo: WAS NOT ON LIST FROM UBA TEAM
Note on D10: hershlin naidoo: WAS NOT ON LIST FROM UBA TEAM
Note on D11: hershlin naidoo: CHECK WITH ALMA
Note on D12: hershlin naidoo: WAS NOT ON LIST FROM UBA TEAM
Note on D13: hershlin naidoo: WAS NOT ON LIST FROM UBA TEAM
Note on A14: hershlin naidoo: COMPLETED BY ALMA
Note on A15: hershlin naidoo: ALMA HAS DONE
Note on D18: hershlin naidoo: WAS NOT ON LIST FROM UBA TEAM
Note on D19: hershlin naidoo: WAS NOT ON LIST FROM UBA TEAM
Note on A20: hershlin naidoo: COMPLETED BY ALMA
Note on A24: hershlin naidoo: DONE BY ALMA
Note on D27: hershlin naidoo: WAS NOT ON LIST FROM UBA TEAM
Note on D28: hershlin naidoo: WAS NOT ON LIST FROM UBA TEAM
Note on D32: hershlin naidoo: WAS NOT ON LIST FROM UBA TEAM